## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Yukta Arun Wagh
Document Created On: | 30-09-2023
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Student Interns Analysis |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Suraj Mane
PROJECT DELIVERABLE | Student Interns Analysis
PROJECT SCOPE
PROJECT START DATE | 31/07/2023
PROJECT END DATE | 30/09/2023
OVERALL PROGRESS | Done
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2024-07-23 | 2024-07-24 | 2 | COMPLETED
| 1.2 Create a project charter |  | 2024-07-25 | 2024-07-27 | 3 | COMPLETED
| 1.3 Requirement gathering |  | 2024-07-28 | 2024-07-31 | 4 | COMPLETED
2 Planning
| 2.1 Baseline project plan |  | 2024-08-01 | 2024-08-05 | 5 | COMPLETED
| 2.2 Plan the design,methods |  | 2024-08-06 | 2024-08-13 | 7 | COMPLETED
3 Execution
| 3.1 Developing |  | 2024-08-14 | 2024-08-22 | 9 | COMPLETED
| 3.2 Testing |  | 2024-08-23 | 2024-08-24 | 3 | COMPLETED
| 3.3 Deployment |  | 2024-08-25 | 2024-08-30 | 6 | COMPLETED
| 4 Closure |  | 2024-09-01 | 2024-09-01 | 1 | COMPLETED